## Project Timeline
E-AUDIT TIMELINE
PROJECT DETAILS
START DATE | END | Working Day | MILESTONE | POSITION | BASELINE
2015-10-05 | 2015-10-22 | 14 | System Requirement & Analyze | 10 | 1
2015-10-23 | 2015-11-19 | 20 | Coding | 10 | 1
2015-11-20 | 2015-12-15 | 18 | Testing | -10 | 1
2015-11-30 | 2015-12-15 | 12 | Documentation | 15 | 1
2015-12-16 | 2015-12-25 | 8 | Training | -15 | 1
2015-12-28 | 2015-12-31 | 4 | Deployment | 15 | 1
Total 60 working day

## Time line 2
|  | E-AUDIT TIMELINE |  | By: Mutiara I-Tech Sdn Bhd
PROJECT DETAILS
START DATE | END DATE | Day | MILESTONE
2015-10-05 | 2015-10-22 | 14 | System Requirement & Analyze
2015-10-23 | 2015-11-19 | 20 | Coding
2015-11-20 | 2015-12-15 | 18 | Testing
2015-11-30 | 2015-12-15 | 12 | Documentation
2015-12-16 | 2015-12-25 | 8 | Training
2015-12-28 | 2015-12-31 | 4 | Deployment
Start
05 Oct '15
Finish
31 Dec '15
11 Oct '15
25 Oct '15
08 Nov '15
22 Nov '15
06 Dec '15
20 Dec '15
System Analysis & Requirement
05 Oct '15 - 22 Oct '15
Development
23 Oct '15 - 19 Nov '15
Testing
20 Nov '15 - 15 Dec '15
Documentation
30 Nov '15 - 15 Dec '15
Training
16 Dec '15 - 25 Dec '15
Deployement
28 Dec '15 - 31 Dec '15